## Sheet1
Kevin McAllister Log Sheet
DATE | EVENT | HOURS
2019-01-10 | Created GitHub repository and Slack Group | 1
2019-01-16 | GROUP MEETING - Added members to Slack and GitHub and decided on general plan for the project | 2
2019-01-18 | Brainstormed game structure and requirements and wrote simple objects for the game | 2
2019-01-23 | GROUP MEETING - Discussed game structure and organized a clear idea of how to write the code | 2
2019-01-24 | Updated objects to match discussed model and set up communication between View and Control | 2
2019-01-25 | Added more objects to store data and updated code with proper names and necessary TODOs | 2.5
2019-01-27 | Substantial code changes, functionality changes and revision on data storage and enum / variable naming | 4
2019-01-31 | GROUP MEETING - Went over Demo requirements and discussed further on the code communication | 1.5
2019-02-01 | Reworked the Observer communication system and cleaned the code | 1.5
2019-02-02 | Added new logic class to process game updated and notify the View | 4
2019-02-03 | Added Strategy class with Operative Random / Next strategies, code bugfixes | 1
2019-02-05 | Added new game functionality, more bug fixes, implemented word loading | 2
2019-02-06 | Set up JUnit testing to test all cases discussed previously (and more) polished parts of the game | 5
2019-02-07 | More cleanup on code, added ability to choose Operative strategy types | 2
32.5
NOTE IM STILL MISSING A FEW MEETINGS BETWEEN ME AND KARIM (HOURS MAY NOT BE 100% ACCURATE)